## Sheet1
Work Estimation Details |  | Optimistic | Most Likely | Pessimistic | Confidence | 75% | 85% | 95% | 99.5% | Supporting Document Links: (Enter Links to Requirements, Specifications, or other supporting documents in this column)
SDLC Phases | Activity/Task (Requirement number) | Effort Hrs | Effort Hrs | Effort Hrs | Factor | Confidence | Confidence | Confidence | Confidence
Construction
| Coding based on priority |  |  |  | 0 | 0 | 0 | 0 | 0
Implementation | REQ 3 (Export schedule) | 8 | 10 | 12 | 0.66667 | 10 | 10.6667 | 11.3333 | 12 | SRS Sec 3.2.3
Implementation | REQ 4 (Course Suggestions) | 10 | 15 | 20 | 1.6667 | 15 | 16.6667 | 18.3333 | 20 | SRS Sec 3.2.4
Implementation | REQ 8 (Create schedule) | 10 | 14 | 18 | 1.3333 | 14 | 15.3333 | 16.6667 | 18 | SRS Sec 3.2.8
Implementation | REQ 10 (Choose completed classes) | 5 | 7 | 10 | 0.83333 | 7.1667 | 8 | 8.8333 | 9.6667 | SRS Sec 3.2.10
[5 empty] | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0
Work Estimate Totals |  | 33 | 46 | 60 |  | 46.1667 | 50.6667 | 55.1667 | 59.6667